## Slide 1
Sprint 1 Review
river_fish — Column-Level Data Lineage · Project RF
Agile delivery metrics for stakeholder review · 30 Jun 2026
Source: live Jira (REST) · multi-agent delivery · synthetic data, real public market data

## Slide 2
Executive Summary
Delivered the full prototype (M1–M7); 2 items carried (externally blocked)
43 / 46
Story Points completed (93%)
16 / 18
stories Done (89%)
~18×
throughput vs human estimate
9.8 h
AI-actual effort (1 session)
18/18 · 20/20
tests · eval green
0
defects escaped to release
+16 SP
scope added mid-sprint (+53%)
2
carried over (deploy, QA)
Headline: a full audit-grade lineage prototype delivered in one session with an AI agent team — quality gates green, governance proven, the only open items blocked on external inputs (HuggingFace credentials, a usage-limit reset).

## Slide 3
Scope & Velocity
30 SP committed · +16 SP emerged · 43 SP delivered
Chart: Sprint 1 — Story Points
| Baseline commit | Scope added | Completed | Carried over
Story Points | 30 | 16 | 43 | 3
▸ Velocity: 43 SP delivered in the sprint window.
▸ Baseline 30 SP — 100% done. Every originally-planned milestone (M1–M7) shipped.
▸ Scope grew +16 SP (+53%) mid-sprint: live market data, gap analysis, the synthetic data platform, deploy-prep, retro & the agent-method demo.
▸ Carried over 3 SP (RF-17 deploy, RF-18 QA re-run) — both blocked on external inputs, not capacity.
▸ Predictability caveat: baseline commitment was fully met; the added scope was unestimated (see Process Findings).

## Slide 4
Estimation & Throughput
Planned-equivalent effort vs. AI-actual
Chart: Effort: 43 SP delivered (hours)
| Planned (human-equiv) | AI-actual
Hours | 172 | 9.8
~18×
throughput acceleration vs. a human-hour estimate (1 SP = 4 h convention).
▸ Planned-equivalent: 43 SP × 4 h = 172 human-hours.
▸ AI-actual logged: 9.8 h (Jira worklogs, epic excluded to avoid roll-up double-count).
▸ Baseline view: 30 SP estimated 120 h → 6.2 h actual = 19.4×.
▸ Estimation accuracy: baseline estimates were directionally sound; the unestimated additions are the gap to close next sprint.

## Slide 5
Quality & Engineering Health
Gated, red-teamed, honest
18 / 18
regression tests
20 / 20
eval (correctness, governance, adversarial)
3
defects caught pre-release (1 High, 2 Med)
0
defects escaped to release
QUALITY PRACTICES
▸ Deterministic, auditable backbone — lineage proven correct vs. hand-authored ground truth.
▸ Governance verified mechanically — eval asserts SQL-text-only; no data rows reach an LLM.
▸ Defects found early — find_node false-match (High) and the lstrip name-corruption (Med) caught and fixed before release.
▸ Independent QA — interim red-team checkpoint; a second independent re-run is scheduled (RF-18).
▸ Honest reporting — the eval harness reports failures rather than hiding them.

## Slide 6
Where the Effort Went
AI-actual minutes by workstream (590 min total)
Chart: Effort by workstream
| Research & Planning | Lineage engine + hardening | LLM / NL + Visualization | Data platform (synth/market/gap) | Eval, Docs & QA | Infra, Deploy, Retro & Reporting
Minutes | 60 | 95 | 140 | 115 | 75 | 105

## Slide 7
Process Findings & Risks
Candid — for the retrospective and next-sprint planning
Process findings
▸ Scope growth unestimated — +16 SP (+53%) added mid-sprint without points; estimate additions up front next time.
▸ Sprints defined but not run — two sprints sit in 'future'; work executed as continuous flow → no native burndown until a sprint is formally closed.
▸ Lead time ≠ effort — ~6 days calendar lead, but ~9.8 h actual effort (bursty/compressed).
▸ Board automation gated — the safety guardrail blocked auto-updating Jira (SP back-fill, sprint close) — needs explicit approval.
Risks / impediments
▸ RF-17 deploy — blocked on HuggingFace account/token (external).
▸ RF-18 QA re-run — blocked on usage-limit reset (10pm IST).
▸ Security — two API tokens were exposed in chat → rotation pending (high priority).
▸ Single-session concentration — delivery depended on one continuous session; spread cadence for resilience.

## Slide 8
Governance & Compliance
Controls held throughout — the basis for an audit conversation
▸ Data boundary — customer/counterparty data 100% SYNTHETIC (DPDP-safe); only PUBLIC market data is real.
▸ On-prem proven — the engine reads SQL text only; no data rows enter an LLM prompt (asserted by the eval harness).
▸ Audit-grade lineage — deterministic parser → DAG; the LLM only explains, labelled 'suggestion — needs sign-off'.
▸ BCBS 239 alignment — attribute (column)-level traceability, the regulatory expectation in the domain.
▸ Human-in-the-loop — sign-off, repository pushes, and all credential handling stayed with the human owner.
Result: speed with governance intact — a repeatable, auditable AI-accelerated delivery model.

## Slide 9
Next Steps & Actions
Owner action in bold
▸ Rotate the two exposed API tokens — HIGH priority security action (owner).
▸ Deploy to HuggingFace (RF-17) — owner provides HF token; keep the public Space $0/key-less.
▸ Independent QA re-run (RF-18) — after the usage-limit reset.
▸ Formalize Sprint 1 in Jira — approve the SP back-fill + sprint close to generate native velocity/burndown (currently gated).
▸ Estimate scope additions up front — carry the retro action to improve predictability.
▸ Sprint 2 candidates — HF deploy, independent QA, the agent-method showcase, and any stakeholder-requested extensions.
river_fish · Sprint 1 · 43/46 SP · 18/18 + 20/20 green · one team, not human-vs-AI